## Slide 1
Q3 Review
July – September 2026 · Performance & Outlook
Prepared for leadership sync · Confidential

## Slide 2
Agenda
• Q3 headline results vs plan
• Revenue, margin, and cash snapshot
• Product & eng delivery highlights
• Customer / ops wins and misses
• Risks, asks, and Q4 priorities

## Slide 3
Q3 headline results
Revenue
₹48.2L
+12% QoQ
Gross margin
41.5%
+1.8 pp
Active users
18.4k
+9% QoQ
NPS
47
+4 pts
• Beat plan on revenue (+₹3.1L vs forecast) driven by renewals and two mid-market wins.
• OpEx held flat; hiring lag kept burn lower than budgeted.
• Support backlog cleared below 48h SLA for the first time this year.

## Slide 4
Financial snapshot
Metric
Q2 actual
Q3 plan
Q3 actual
vs plan
Revenue (₹L)
43.0
45.1
48.2
+6.9%
COGS (₹L)
26.2
26.8
28.2
+5.2%
Gross profit (₹L)
16.8
18.3
20.0
+9.3%
OpEx (₹L)
14.1
15.0
14.4
-4.0%
Operating income (₹L)
2.7
3.3
5.6
+69%

## Slide 5
Product & engineering delivery
• Shipped: offline-first sync v2, billing redesign, and onboarding checklist (activation +11%).
• Reliability: p99 latency -18%; error budget burn stayed under 30% for the quarter.
• Debt: cut critical security tickets from 14 to 3; remaining 3 scheduled for Oct.
• Miss: partner marketplace still in private beta (slipped 4 weeks) — root cause: contract review lag.

## Slide 6
Customers & operations
• Wins: 2 mid-market logos (AlphaCorp renew + BetaTech expansion); logo churn 1.4%.
• CSAT 4.6/5 on ticket surveys (n=312); top praise = response speed.
• Misses: one enterprise pilot stalled on SSO; recovery plan owned by Solutions (due Oct 15).
• Ops: support macros rewritten; first-contact resolution up to 62%.

## Slide 7
Risks, asks & Q4 priorities
• Risk: cloud cost spike if Diwali traffic doubles — need reserved capacity.
• Ask: approve 2 eng hires (mobile + data) already in Q4 plan; start interviews next week.
• Q4 priority 1: marketplace GA + SSO package for enterprise.
• Q4 priority 2: cut gross churn below 1.0% with at-risk playbook.
• Q4 priority 3: usage-based billing pilot to 20 customers by Dec 15.

## Slide 8
Thank you
Questions & discussion
Q3 Review · Jul–Sep 2026